## Zone wise expenditure detail 08
Expenditure status of Infrastructure proposals (Rs. In Crores) as on 03.01.2022
S. No. | Smart Infra Unique -ID | Zone | Comm'te | Proposal in Brief | Branch | Total Project Cost | Expenditure till F.Y. 2020-21 | Actual funds released in F.Y. 2021-22 | S.O. No. & Date (F.Y. 2021-22) | Date on which funds are released | Whether LoA issued: Yes/No | Date of LoA | Expenditure till date | Expenditure yet to be incurred
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 10 | 11 | 12 | 13 | 14
1 | 002-16 | Ahmedabad Customs | Jamnagar | Construction of office building at Jamnagar | Construction | 43.67 | 28.7 | 10 | Const./05/Sanction/2021-22 18.06.2021 & Const./36/Sanction/2021-22 18.11.2021 | 22.06.2021 & 22.11.2021 | Yes | 05.07.2021 & 16.08.2021 | 7.5 | 2.5
2 | 006-18 | Ahmedabad Customs | Ahmedabad | Construction of Office building cum Guest house for Customs Department at the site of Shore Guard, Dwarka, Jamnagar | Construction | 1.24 | 0.4 | 0.5 | Const./03/Sanction/2021-22 07.06.2021 | 09.06.2021 | Yes | 21.06.2021 | 0.48 | 0.02
3 | 008-20 | Bengaluru CGST | Mangalore | A/a & e/s of Rs. 22,66,000/- for replacement of DG set with AMF panel and acoustic enclosure, damaged HT Panel, defective cables, and servicing of 500 KVA transformer at C.R. Building, Attavara, Mangalore-reg | R&M | 0.23 | .- | 0.23 | 30/2021-22 01.07.2021 | 07.07.2021 | Yes | 02.08.2021 | 0 | 0.23
4 | 233-18 | Bengaluru CGST | CGST Bengaluru North West | Revalidation of special repairs to Central Revenue office buiding (Central Excise & Income Tax Dept. At Davanagere. | R&M | 0.68 | .- | 0.02 | 77/2021-22 10.09.2021 | 20.09.2021 | No | NA | NA | 0.02
5 | 418-19 | Bengaluru CGST | Bengaluru South Bengaluru | Upgradation of 17 flats in Akshaya Apartments for Central Excise and Customs, Malleshwaram, Bangalore including electrical provisions. | R&M | 3.55 | .- | 1.55 | 124/2021-22 17.11.2021 | 23.11.2021 | Yes | 16.12.2021 | NA | 1.55
6 | 200-18 | Bengaluru CGST | CGST Mangaluru | (UID 200-18) Revalidation of proposal seeking a/a & e/s for an estimate cost of Rs.2,49,96,500/- for upgradation of 73 C.Ex. Qtrs. (15 Type-I, 15 Type-II, 30 Type-III, 8 Type-IV and 4 Type-V) at Kankanady, Mangaluru-reg. | R&M | 2.21 | .- | 2.21 | 143/2021-22 01.12.2021 | 08.12.2021 | No | NA | NA | 2.21
7 | 434-19 | Bhopal CGST | CGST Bhopal | (UID 434-19) Proposals for modernization of 1 No.13 passengers Lift i/c renovation of toilet, P/F of LED signage board, Water Purfier with water cooler in GF etc. for CGST Building at Bhilai-reg. | R&M | 0.23 | .- | 0.23 | 131/2021-22 24.11.2021 | 02.12.2021 | No | NA | NA | 0.23
8 | 282-19 | Bhubaneswar CGST | CGST Bhubaneswar | (UID 282-19) Revalidation of A/A & E/s of Rs.4,24,92,000/- for special repair work of departmental residential building (C.R. Colony), Rajaswa Vihar, Bhubaneswar (Post FANI Cycloe)-reg. | R&M | 4.25 | .- | 1.5 | 119/2021-22 15.11.2021 | 18.11.2021 | No | NA | 0 | 1.5
9 | 017-20 | Chandigarh CGST | Srinagar | Construction of boundary wall with barbed wire fencing around the land at Solina, Srinagar purchased for construction of office and residential building of customs & CGST Division, Srinagar | Construction | 4.14 | 0 | 0.5 | Const./25/Sanction/2021-22 18.08.2021 | 25.08.2021 | Yes | 07.09.2021 | 0.02 | 0.48
10 | 019-20 | Chennai CGST | CGST Chennai Audit-I Chennai | Revalidation of replacement of 2 Nos. of 40 KVA Online 3 Phase UPS system with 30 minutes backup i/c batteries, etc-reg. | R&M | 0.19 | .- | 0.19 | 17/2021-22 15.06.2021 | 24.06.2021 | Yes | 09.11.2021 | 0 | 0.19
11 | 024-20 | Chennai CGST | CGST Chenani North | Replacing of 25 years old 200 KVA & 125 KVA DG sets with upgraded 500 KVA silent type DG set for Chennai North Comm'te-reg. | R&M | 0.54 | .- | 0.54 | 27/2021-22 25.06.2021 | 30.06.2021 | Yes | 16.07.2021 | 0.15 | 0.39
12 | 087-19 | Chennai CGST | CGST Puducherry | Revalidation of Renovation of Old Light House in Puducherry-Nomination of M/s. INTACH, Puducherry as Consultant-(Total project cost may be 3 cr., initially an amount of 1.5 cr may be released). | R&M | 3.32 | .- | 1.09 | 39/2021-22 19.07.2021 | 26.07.2021 | Yes | Not Found | 0 | 1.09
13 | 033-20 | Chennai CGST | CGST Trichy | Conversion of overhead lines into underground HT Cable for service connection including dismantling of overhead lines and poles at Hqrs. Building, No.1, Williams Road, Contonment Trichy-reg. | R&M | 0.65 | .- | 0.6 | 44/2021-22 20.07.2021 | 29.07.2021 | Yes | 25.10.2021 | 0 | 0.6
14 | 034-20 | Chennai CGST | CGST Chennai North | Revalidation of augementation of exsiting obsolete and worn out fire detection and alaqrm system (CONVENTIONAL) at C.Ex. (main & Annexe) building, Nungambakkam, Chennai-reg. | R&M | 0.47 | .- | 0.08 | 46/2021-22 22.07.2021 | 29.07.2021 | Yes | 02.12.2021 | 0 | 0.08
15 | 037-20 | Chennai CGST | CGST Chennai Chennai North | Revalidation of augementation of exsiting obsolete and worn out fire fighitng down comer system at C.Ex. (Main & Annexe) Building, Nungambakkam, Chennai-reg. | R&M | 0.45 | .- | 0.45 | 54/2021-22 28.07.2021 | 06.08.2021 | Yes | 03.11.2021 | 0 | 0.45
16 | 003-20 | Chennai CGST | CGST Puducherry | Revalidation of up-gradation of C.Ex. Residential quarters at, Puducherry- forwarding of proposal Grant of A/A & E/S-reg. | R&M | 4.9 | .- | 1 | 18-2021-22 15.06.2021 | 21.06.2021 | Yes | 16.07.2021 | 0 | 1
17 | 300-21 | Chennai CGST | CGST Puducherry Chennai | (UID 300-21) A/a & E/s of Rs. 57,56,000/- for Providing Accessible India facilities in Customs & Central Excise office at Beach road, Karaikal SH: Providing Lift i/c construction of lift Shaft, Toilet For Physically challenged & Ramp | R&M | 0.58 | .- | 0.58 | 123-2021-22 16.11.2021 | 29.11.2021 | Yes | 09.12.2021 | 0 | 0.58
18 | 225-20 | Chennai CGST | CGST Madurai | (UID 225-20) Administrative approval and expenditure sanction for purpose of provision of lift facility in Madurai divisional office building as per the impelementation of Accessible India campaign involving a total expenditure of Rs. 44,76,300/- | R&M | 0.45 | .- | 0.45 | 147-2021-22 02.12.2021 | 09.12.2021 | Yes | NF | 0 | 0.45
19 | 169-17 | Chennai CGST | CGST Madurai | (UID 169-17) Revalidation of Upgradation and repair of division office Bldg.at Rajapalayam for a total expenditure of Rs 1,46,04,000/-. | R&M | 1.46 | .- | 0.32 | 144-2021-22 02.12.2021 | 08.12.2021 | No | NA | 0 | 0.32
20 | 001-16 | Chennai Cus. | Chennai | Construction of residential qtrs. at Anna Nagar, Chennai. | Construction | 348.77 | 124 | 80 | Const./06/Sanction/ 2021-22 15.06.2021 | 17.06.2021 | Yes | 30.06.2021 | 79.91 | 0.09
21 | 001-18 | Chennai Cus. | Chennai | Construction of 36 residential quarters at Nungambakkam, Chennai | Construction | 49.02 | 4.7 | 10 | Const./07/Sanction/ 2021-22 18.06.2021 | 22.06.2021 | Yes | 30.06.2021 | 0.14 | 9.86
22 | 415-20 | Data Management | Data Management | Requirement of funds for S.I.T.C. of silent type DG Set and UPS system in the premises of the Directorate of Data Management located in 'A' Wing 3rd Floor, Pushpa Bhawan, New Delhi under the head minor works during the current F.Y. 2019-20-reg. | R&M | 0.58 | .- | 0.2 | 103/2021-22 20.10.2021 | 10.11.2021 | Yes | 24.11.2021 | 0 | 0.2
23 | 253-07 | Delhi CGST | Delhi (West) | Payment for providing in new load of 1408KW having BP No. 907775367 at Plot No. 1, Retail Business Centre, Nangal Raya, Janakpuri, New Delhi | Construction | 4.03 | 32.83 | 4.03 | Const./20/Sanction/2021-22 16.07.2021 & Const./32/Sanction/2021-22 01.10.2021 | 29.07.2021 & 12.10.2021 | Non-LoA case | NA | 4.03 | 0
24 | 001-17 | Delhi CGST | Delhi North | Construction of residential qtrs. at Dwarka | Construction | 227 | 107.25 | 40 | Const./02/Sanction/ 2021-22 07.06.2021 | 09.06.2021 | Non-LoA case | NA | 40 | 0
25 | 117-17 | Delhi CGST | CGST Delhi North | Revalidation of providing Comprehensive repair to multi-stories residential Shipra Tower of C.Ex. Department at Vaishali, Ghaziabad for total expenditure of Rs.6,38,93,701/-. | R&M | 6.39 | 3.11 | 3.28 | 11/2021-22 04.06.2021 | 17.06.2021 | Yes | 14.07.2021 | 0 | 3.28
26 | 330-20 | Delhi CGST | CGST Delhi | Demolition of Residential Kaveri Tower of C.Ex. Department, Vaishali, Ghaziabad during 2019-20-reg. | R&M | 0.81 | 0.81 | 0.81 | 166/2021-22 22.12.2021 | 24.12.2021 | No | NA | 0 |  | Not Found
27 | 001-19 | Delhi Cus. Prev. | Jodhpur Cus. (P) | Revalidation of A/a & F/s of Rs.4,14,50,000/- for upgradation and renovation of residential quarters Type-I, Type-II, Type-III, Type-IV & Type-V with roads and sewerage work in residenital colony at Jodhpur-reg. | R&M | 3.95 | .- | 0.95 | 38/2021-22 16.07.2021 | 26.07.2021 | Yes | 14.09.2021 | 0.64 | 0.31
28 | 244-19 | Delhi Customs | (Delhi Airport & General) | Construction of one lift well for 8 nos. passenger lift at New Custom House Near IGI Airport, New Delhi. | R&M | 0.44 | .- | 0.16 | 100/2021-22 13.10.2021 | 20.10.2021 | Yes | 15.12.2021 | 0 | 0.16
29 |  | Delhi Customs (Prev.) | Amritsar Customs (Prev.) | Construction of new Customs Post at Swarnjayanti Gate at Attari Border - Deployment of new X-ray Baggage Inspection Systems (XBIS) | Construction | 0.48 | _ | 0.48 | Const./41/Sanction/2021-22 06.12.2021 | 27.12.2021 | No | NA | 0 | 0.48
30 | 003-16 | DRI | DRI Kolkata | Construction of DRI office Building at Kolkata | Construction | 64.5 | 9.5 | 10 | Const./15/Sanction/2021-22 25.06.2021 | 30.06.2021 | Yes | 15.07.2021 | 4.16 | 5.84
31 | 036-20 | DRI | Lucknow | Construction of boundary wall by DRI Zonal Unit, Lucknow | Construction | 0.98 | 0.4 | 0.58 | Const./08/Sanction/2021-22 18.06.2021 | 24.06.2021 | Yes | 16.07.2021 | 0.32 | 0.26
32 | 023-20 | DRI | DRI Chennai | Construction of office building of DRI Zonal Unit at Trustpuram Kodambakkam, Chennai | Construction | 31.38 | NA | 0.1 | Const./17/Sanction/2021-22 29.06.2021 | 07.07.2021 | No | __ | 0 | 0.1
33 | 212-19 | DRI Delhi | DRI (HQ.) | Construction of office building for DRI (HQ.) at Vasant Kunj, Delhi | Construction | 74.8 | NA | 0.1 | Const./29/Sanction/2021-22 03.09.2021 | 08.09.2021 | No | ___ | 0 | 0.1
34 | 001-15 | Guwahati CGST | Agaratala | Construction of office building for CGST Comm'te, Customs Divisions and Agartala Audit Circle at Agartala | Construction | 28.04 | 9 | 8 | Const./24/Sanction/2021-22 13.08.2021 | 24.08.2021 | Yes | 18.10.2021 (6.5) 20.10.2021 (1.50) | 4.89 | 3.11
35 | 235-20 | Guwahati CGST | Customs Prev. Guwahati | Replacement of the two lifts in the office premises and residential complex at Custom House, Guwahati-reg. | R&M | 0.4 | 0 | 0.4 | 115/2021-22 28.10.2021 | 29.10.2021 | No | NA | 0 | 0.4
36 | 005-16 | Hyderabad Customs | Hyderabad | Construction of compound wall & office building at Mamidipally, Near Shamshabad Airport, Hyderabad. | Construction | 1.3 | 0.32 | 0.6 | Const./12/Sanction/2021-22 23.06.2021 | 28.06.2021 | Yes | 10.08.2021 | 0.35 | 0.25
37 | 085-19 | Jaipur CGST | Udaipur | Construction of new office building for Udaipur CGST office at Udaipur including GH | Construction | 42.06 | 0.6 | 8 | Const./11/Sanction/2021-22 18.06.2021 | 21.06.2021 | Yes | 05.07.2021 | 7.05 | 0.95
38 | 122-11 | Jaipur CGST | Udaipur | Construction of office building for 02 division, 04 newly created CGST Ranges and Audit Circle at Bhilwara CGST, Udaipur Comm'te | Construction | 9.72 | 3.5 | 4.52 | Const./18/Sanction/2021-22 29.06.2021 | 07.07.2021 | Yes | 07.07.2021 | 3.92 | 0.6
39 | 231-19 | Jaipur CGST | Jaipur | Construction of RCC retaining wall in GST Colony along with back Nallah at JLN Marg, Jaipur | Construction | 1.16 | 0.28 | 0.88 | Const./04/Sanction/ 2021-22 15.06.2021 | 24.06.2021 | Yes | 23.06.2021 | 0.88 | 0
40 | 243-13 | Kolkata Custom | (Kolkata (AP & ACC)) | Renovation work of Custom House Kolkata (Heritage Building) by INTACH-reg. | R&M | 62.86 | 1.32 | 5 | 59/2021-22 03.08.2021 | 13.08.2021 | Yes | 01.12.2021 | 0 | 5
41 | 106-20 | Kolkata Zone CGST | CGST Bolpur | Revalidation of a/a & e/s for following works in C.R. Building City Center, Durgapur, Bolpur. (i) Enhancing electric load connection from 47KVA to 106 KVA. (ii) Construciton of electric meter room (10x10x10feet). (iii) Laying of vable and replacement of old panel by new panel due to enhancement of load. (iv) Up-gradation of wiring infrastructure. | R&M | 0.35 | .- | 0.35 | 29/2021-22 25.06.2021 | 30.06.2021 | No | NA | 0 | 0.35
42 | 238-13 | Lucknow CGST | Allahabad | Construction of boundary wall on plot allocated to CGST and CX Division Raebareilly, CGST & CX Commissionerate, Allahabad | Construction | 0.29 | NA | 0.29 | Const./21/Sanction/2021-22 04.08.2021 | 13.08.2021 | Yes | 08.09.2021 | 0 | 0.29
43 | 307-19 | Lucknow CGST | Agra | Const. of new office building for CGST Division at Aligarh. | Construction | 13.08 | NA | 0.01 | Const./39/Sanction/2021-22 02.12.2021 | 09.12.2021 | No | ___ | 0 | 0.01
44 | 143-17 | Meerut CGST | Ghaziabad | Construction of office building including boundary wall for CGST Ghaziabad, Audit-II, Ghaziabad, Noida | Construction | 116.42 | 2.53 | 10 | Const./13/Sanction/2021-22 18.06.2021 | 21.06.2021 | Yes | 16.07.2021 | 9.99 | 0.01
45 | 151-16 | Mumbai CGST | Palghar | Construction of 3 Div. offices and 14 ranges offices at Boisar | Construction | 33.25 | 3.12 | 10 | Const./14/Sanction/2021-22 22.06.2021 | 24.06.2021 | Yes | 27.07.2021 | 5.42 | 4.58
46 | 222-15 | Mumbai CGST | Raigad | Construction of residential qtrs. at Kharghar by NBCC. | Construction | 110.11 | 41.67 | 25 | Const./10/Sanction/ 2021-22 18.06.2021 | 24.06.2021 | Non-LoA case | NA | 20 | 5
47 | 003-15 | Mumbai CGST | CGST Mumbai Central | Revalidation of an amount of Rs. 1,17,96,414/- for construction of boundary wall for C.Ex. Department at Bhandup (East). | R&M | 1.18 | .- | 0.2 | 02/2021-22 25.05.2021 | 03.06.2021 | No | NA | 0 | 0.2
48 | 123-19 | Mumbai CGST | CGST Mumbai Central | Revalidation of Extra Ordinay structural reapir and other misc. work for building no.3 and 5, CGS Colony, Bhandup (e) Mumbai of C.Ex. Department. | R&M | 0.99 | .- | 0.11 | 12/2021-22 04.06.2021 | 16.06.2021 | No | NA | 0 | 0.11
49 | 002-17 | Mumbai CGST | CGST Mumbai Central Mumbai | Revalidation of revised preliminary estimate for Providing Sewage Treatment Plant at Sector-A,, CGS Colony, Bhandup (East), Mumbai. | R&M | 0.6 | .- | 0.29 | 25/2021-22 17.06.2021 | 24.06.2021 | Yes | 18.10.2021 | 0 | 0.29
50 | 003-14 | Mumbai CGST | CGST Mumbai Central | Revalidaion of structural repairs and Aesthetic improvement to Central Excise quarters at Sector-VII, S.M. Plot, Antop Hill, Mumbai-37 during 2013-14. Sh: Structural repair and External painting to building No.52 of C.Ex. (Type-II, 60 Nos. Qtrs)-reg. | R&M | 0.77 | .- | 0.13 | 41/2021-22 20.07.2021 | 29.07.2021 | Yes | NA | 0 | 0.13
51 | 130-19 | Mumbai CGST | CGST Mumbai Central | Revalidaiton of Repairing of Controal Room & Driver's Room, GST Bhavan, Churchgate, Mumbai-reg. | R&M | 0.25 | .- | 0.11 | 51/2021-22 23.07.2021 | 29.07.2021 | No | NA | 0 | 0.11
52 | 158-18 | Mumbai CGST | CGST Mumbai Central | Revalidaiton of Upgradation & Renovation of 20 Nos. Type-III C.Ex./CGST qtrs. at Gorai, Boriwali, Mumbai. | R&M | 0.91 | .- | 0.4 | 57/2021-22 03.08.2021 | 12.08.2021 | Yes | 18.10.2021 | 0 | 0.4
53 | 218-19 | Mumbai CGST | CGST Mumbai | Replacement of 2 Number of lift in the GST Bhawan. | R&M | 0.65 | .- | 0.65 | 58/2021-22 29.07.2021 | 12.08.2021 | Yes | 06.09.2021 | 0 | 0.65
54 | 214-21 | Mumbai CGST | CGST Mumbai Central | A/a & E/s of Rs. 81,60,800/- for Structural repairs including exterior painting to 19 Nos. Bldg.: Central Excise, BKC, Mumbai-reg. | R&M | 0.82 | .- | 0.82 | 92/2021-22 28.09.2021 | 05.10.2021 | Yes | 01.12.2021 | 0 | 0.82
55 | 281-21 | Mumbai CGST | CGST Mumbai | (UID 281-21)A/a & E/s of Rs. 7,13,500/- for Conducting Structural Audit of Residential Buildings No. 26 & 27 of CGST Deptt. at Oshiwara, Andheri (W), Mumbai-reg. | R&M | 0.07 | .- | 0.07 | 109/2021-22 21.10.2021 | 02.11.2021 | Yes | NF | 0 | 0.07
56 | 326-20 | Mumbai CGST | CGST Mumbai | (UID 326-20) A/a & e/s for up-gradation of Internal E.I. of 34 Nos. Type-I qtrs. of building No.47 (Central Excise Pool qtrs.)-reg. | R&M | 0.29 | .- | 0.29 | 146/2021-22 02.12.2021 | 09.12.2021 | No | NA | 0 | 0.29
57 | 360-20 | Mumbai CGST | CGST Thane Mumbai | (UID 360-20) Administrative Approval & Expenditure Sanction of Rs. 49,62,525/- for the work of repairing, reconstruction and increasing height of the boundary wall for the Government's plot bearing city Survey No. 37 & 38 A situated near Kalwa Bridge, and m the custody of CGST & Central Excise, Thane Cotnmissionerate | R&M | 0.5 | .- | 0.5 | 148/2021-22 02.12.2021 | 08.12.2021 | Yes | NA | 0 | 0.5
58 | 429-21 | Mumbai CGST | CGST Raigad | (UID 429-21) A/a & E/s of Rs. 45,54,954/- for Replacemcnt or rising main and panvel in CGST Raigad. New Panvel-reg. | R&M | 0.46 | .- | 0.46 | 132/2021-22 24.11.2021 | 01.12.2021 | Yes | NA | 0 | 0.46
59 | 229-16 | Mumbai Cus-I | Mumbai (Gen.) | Construction of residential quarters at Customs Enclave Plot, Wadala, Mumbai | Construction | 480 | 0.1 | 5 | Const./16/Sanction/2021-22 25.06.2021 | 30.06.2021 | Yes | 03.09.2021 | 0.8 | 4.2
60 | 229-16 | Mumbai Cus-I | Mumbai (Gen.) | Construction of Office complex at Customs Enclave Plot, Wadala, Mumbai | Construction | 495.75 | 0.1 | 5 | Const./16/Sanction/2021-22 25.06.2021 | 30.06.2021 | Yes | 01.11.2021 | 0 | 5
61 | 213-19 | Mumbai Cus-I | (Mumbai Cus (General)) | Revalidation of providing & fixing sliding windows to 48 Nos. qtrs. Of C.Ex. & Customs Department at Katrak Road, Wadala, Mumbai Rs.83,79,308/- | R&M | 0.84 | .- | 0.21 | 96/2021-22 13.10.2021 | 28.10.2021 | Yes | 13.12.2021 | 0 | 0.21
62 | 305-18 | Mumbai Cus-I | (Mumbai Cus (General)) | Revalidation of Construction of compound wall at Gholwad office, Bassein Division. | R&M | 0.79 | .- | 0.79 | 102/2021-22 20.10.2021 | 16.11.2021 | No | NA | 0 | 0.79
63 | 279-21 | Mumbai Cus-I | (Mumbai Cus (General)) | A/a & e/s of Rs. 6,34,940/- for Conducting Structural Audit along with Remedial measures of Custom and Central excise Qtrs at Katrak Road, Wadala(W}, Mumbai-reg. | R&M | 0.06 | .- | 0.06 | 111/2021-22 21.10.2021 | 02.11.2021 | Yes | 13.12.2021 | 0 | 0.06
64 | 449-21 | Mumbai Cus-I | Mumbai-I Customs (Mumbai Cus (General)) | (UID 449-21) Preliminary Estimate of up gradation of open areas and parking areas in Custom Colony, Five Garden, Matunga, Mumbai. | R&M | 0.99 | .- | 0.99 | 163/2021-22 20.12.2021 | 23.12.2021 | No | NA | 0 | 0.99
65 | 230-21 | Mumbai Customs Zone-II | Mumbai -II JNCH Nhava Sheva | A/A & E/s of Rs. 90,19,821/- for providing sprinkler system in the office building and gas based Fire suppression system in servent room at JNCH, Nhava Sheva. | R&M | 0.9 | .- | 0.9 | 101/2121-22 20.10.2021 | 16.11.2021 | No | NA | 0 | 0.9
66 | 280-21 | Mumbai -I Cus | Mumbai -I Cus | (UID 280-21) A/a & E/s of Rs. 18,76,200/- for Conducting Structural Audit along with remedial measures for Custom Department Qtrs. at Five garden, Matunga, Mumbai-reg. | R&M | 0.19 | .- | 0.19 | 121/2021-22 17.11.2021 | 23.11.2021 | Yes | 20.12.2021 | 0 | 0.19
67 | 401-16 | NACIN | NACIN | Construction of New Academy of NACIN at Palasamudram (V), (Hindupur) Ananthpur Dist., Andhra Pradesh (boundary wall & gate complex) | Construction | 15.14 | 10.35 | 3 | Const./19/Sanction/2021-22 02.07.2021 & Const./40/Sanction/2021-22 15.12.2021 | 02.07.2021 & 15.12.2021 | Yes | 03.09.2021 | 0.15 | 2.85
68 | 401-16 | NACIN | NACIN | Construction of New Academy of NACIN at Palasamudram (V), (Hindupur) Ananthpur Dist., Andhra Pradesh (Consultancy work) | Construction | 2 | NA | 2 | Const./01/Sanction/2021-22 15.06.2021 | 22.06.2021 | Yes | 06.08.2021 | 1.24 | 0.76
69 | 205-13 | NACIN | Hyderabad | Construction of RTI NACIN at Attapur, Hyderabad | Construction | 46.71 | 42.85 | 3.5 | Const./34/Sanction/2021-22 18.11.2021 | 22.11.2021 | Non-LoA case | NA | 0 | 3.5
70 | 139-19 | NACIN | NACIN -FBD | Revalidaiton of a/a & E/s of fund of Rs. 1,75,10,700/- for renovation of Mandakani hostel at NACIN, Sector-29, Faridabad-reg. | R&M | 1.75 | .- | 0.57 | 26/2021-22 18.06.2021 | 24.06.2021 | Yes | 06.08.2021 | 0.48 | 0.09
71 | 092-20 | Nagpur CGST | CGST Nagpur-I | A/a & e/s for installation of wet riser system in GST Bhavan at Civil Lines, Nagpur-reg. | R&M | 0.68 | .- | 0.68 | 28/2021-22 25.06.2021 | 30.06.2021 | Yes | 29.11.2021 | 0 | 0.68
72 | 094-19 | Nagpur CGST | CGST Nashik (Audit) | Revalidation of submission of PE of Rs.1,65,31,246/- for major repairs of the office building of Commissioner of CGST & C.Ex., Audit Nashik Comm'te, Nashik at Gadkari Chowk, Nashik-reg. | R&M | 1.65 | .- | 0.25 | 31/2021-22 01.07.2021 | 07.07.2021 | Yes | 22.11.2021 | 0 | 0.25
73 | 237-19 | Nagpur CGST | Nagpur-I | Revalidation of propsoal for total renvoation followed by installation of Cbicles including tilling and window repalcement for preventive Room at GF, Room No. 109 at FF and Room No. 313 at TF of GST Bhavan, Civil Lines, Nagpur involving and expenditure of Rs.80,67,800/- | R&M | 0.81 | .- | 0.1 | 71/2021-22 13.08.2021 | 19.08.2021 | Yes | 26.11.2021 | 0 | 0.1
74 | 004-14 | Patna Cus. | Patna Cus. (Prev.) | Construction of 21 nos. of staff quarters, guest House/ Multi-purpose Hall and Boundary wall at LCS, Raxaul | Construction | 11.85 | 5.8 | 4.66 | Const./28/Sanction/2021-22 18.08.2021 | 24.08.2021 | Yes | 07.10.2021 | 0.5 | 4.16
75 | 004-16 | Patna Cus. | Patna Cus. (Prev.) | Construction of Residential complex at Land Customs Station jogbani | Construction | 7.99 | 2.59 | 1 | Const./27/Sanction/2021-22 18.08.2021 | 24.08.2021 | Yes | 11.10.2021 | 0.33 | 0.67
76 | 002-15 | Pune CGST | Kolhapur | Construction of office building for CGST Commissionerate Kolhapur, at Tarabai Park, Kolhapur | Construction | 42.44 | 0.1 | 6 | Const./09/Sanction/2021-22 18.06.2021 | 24.06.2021 | Yes | 12.07.2021 | 1.71 | 4.29
77 | 008-18 | Pune CGST | Pune-II | Construction of office building and staff quarters for CGST Range offices at Pandharpur, Dist. Solapur, Maharasthra | Construction | 2.05 | 0.51 | 1.5 | Const./22/Sanction/2021-22 04.08.2021 | 13.08.2021 | Yes | 25.10.2021 | 0.28 | 1.22
78 | 404-21 | Pune CGST | Goa Cus. | Demolition of dilapidated 08 Nos. Type III Quarters (G+3 Building 01 block bearing Q. No. 117 to 124) at Custom Colony, Headland Sada, Vasco, Goa | Construction | 0.09 | 0 | 0.09 | Const./30Sanction/2021-22 29.09.2021 | 05.10.2021 | Yes | 24.11.2021 | 0 | 0.09
79 | 035-20 | Pune CGST | Goa-Cus. | Revalidation of repairs to exisintg roofing and other miscellaneious works for Custom Guest House, Panaji, Goa. | R&M | 0.23 | .- | 0.23 | 16/2021-22 09.06.2021 | 21.06.2021 | Yes | 14.07.2021 | Not Found | 0.2
80 | 104-20 | Pune CGST | CGST Kolhapur | Revalidation of Up-gradation and repairs to 10 nos. Type-II residential quarters of CGST Department at tarabai Park, Kolhapur (Maharashtra)-reg. | R&M | 0.85 | .- | 0.85 | 19/2021-22 15.06.2021 | 24.06.2021 | Yes | 12.07.2021 | Not Found | 0.85
81 | 160-20 | Pune CGST | CGST Kolhapur | Proposal for upgradation and repairs to 24 nos. Type-III residential quarters of CGST Department at tarabai park, Kolhapur (Maharashtra)-reg. | R&M | 1.86 | .- | 0.86 | 82/2021-22 17.09.2021 | 30.09.2021 | Yes | 21.10.2021 | Not Found | 0.86
82 | 224-20 | Pune CGST | Goa-Cus. | Setting up of Indian Customs & Indirect taxes Museum Goa Through INTACH-reg. | R&M | 1.89 | .- | 1.89 | 104/2021-22 20.10.2021 | 02.11.2021 | No | NA | 0 | 1.89
83 | 204-18 | Pune CGST | CGST Pune | Revalidaiton proposal for construction of lift and Unisex Accessible Toilets and Ramp for differently abled persons in GST Office, Miraj, Sangli District, Maharashtra. | R&M | 0.63 | .- | 0.14 | 127/2021-22 23.11.2021 | 02.12.2021 | No | NA | 0 | 0.14
84 | 340-21 | Ranchi CGST | Ranchi | Proposal for (i) Topographical Survey & Soil Investigation (Rs. 91,200/-) and (ii) Construction of boundary wall, main gate & guard room at HEC area, Nagri, Ranchi (Rs. 1,54,63,000/-) | Construction | 1.55 | NA | 0.21 | Const./38/Sanction/2021-22 30.11.2021 | 15.12.2021 | No | ___ | 0 | 0.21
85 | 015-20 | Ranchi CGST | CGST Patna-I | Revalidaiton of replacement of window tile UPVC window from ground floor to 4th floor at C.R. Building (Annexe), Birchand Patel Path, Patna-reg. | R&M | 0.63 | .- | 0.62 | 49/2021-22 23.07.2021 | 29.07.2021 | Yes | 26.11.2021 | 0 | 0.62
86 | 183-21 | Ranchi CGST | CGST Patna-II | A/a & E/s of Rs. 80,65,985/- for Renovation of existing sewer line, Drain, Road, Main water Supply line for Custom & Central Excise Office and Residential | R&M | 0.81 | .- | 0.81 | 80/2021-22 13.09.2021 | 17.09.2021 | Yes | 29.11.2021 | 0 | 0.81
87 | 246-19 | Ranchi CGST | CGST Patna-I | Revalidation of Providing of Automatic fire alram system at Central Revenue Building (Annexe), Bir Chand Patel Path, Patna-reg. | R&M | 0.3 | .- | 0.18 | 90/2021-22 27.09.2021 | 05.10.2021 | Yes | 26.11.2021 | 0 | 0.18
88 | 412-21 | Ranchi CGST | CGST Patna-II | A/a & e/s of Rs. 62,12,165/- for providing fire fighting system in Customs & CGST -office, Imlichatti, Muzaffarpur, Bihar-Reg | R&M | 0.62 | .- | 0.2 | 91/2021-22 27.09.2021 | 05.10.2021 | No | NA | 0 | 0.2
89 | 306-19 | Ranchi CGST | CGST Patna-I | Revalidation of Submission of proposals requring a/a & e/s for repari & maintenance of SITC of 13 passenger lift (G+6 at C.R. Building (Annexe), B.C. Patel Path, Patna-reg. | R&M | 0.73 | .- | 0.23 | 104/2021-22 20.10.2021 | 02.11.2021 | No | NA | 0 | 0.23
90 | 417-21 | Ranchi CGST | CGST Patna-II | (UID 417-21) A/a & e/s of Rs. 64,92,600/- for Providing 13 Passenger Lift in Custom and Central Excise building at Muzaffarpur-reg. | R&M | 0.65 | .- | 0.65 | 134/2021-22 24.11.2021 | 02.12.2021 | No | NA | 0 | 0.65
91 | 203-20 | Thiruvananthapuram CGST | CGST Thiruvananthapuram | One time speical repair-renovation of toilets (Civil and Electrical Works) at CGST & Central Excise Comm'te, CGST Bhavan, Thiruvananthapuram-reg. | R&M | 0.72 | .- | 0.15 | 66/2021-22 06.08.2021 | 19.08.2021 | Yes | 24.09.2021 | 0 | 0.15
92 | 426-21 | Thiruvananthapuram CGST | CGST Thiruvananthapuram | (UID 426-21) A/a & E/s of Rs. 20,78,100/- fro implementation of Accessible India Campaign. SH: Construction of ramp at entrance of main building and conversion of existing Gents toilet at Ground floor for Divyangjan at GST Bhavan, Trivandrum-reg. | R&M | 0.21 | .- | 0.21 | 133/2021-22 24.11.2021 | 02.12.2021 | No | NA | 0 | 0.21
93 | 164-21 | Thiruvananthapuram CGST | CGST Thiruvananthapuram | (UID 164-21) A/a & E/s of Rs.40,43,200/- for providing curtain rods, paver blocks, and mosquito net shutter, qater proofing to roof of all blocks in C.Ex., staff residential quarters, Thrikkakkara-reg. | R&M | 0.4 | .- | 0.4 | 154/2021-22 15.12.2021 | 16.12.2021 | No | NA | 0 | 0.4
94 | 002-14 | Tiruchirappalli (P.) Zone | Tuticorin | Construction of 6 nos. additional residential quarters at Port Area, Tuticorin | Construction | 1.62 | 1.11 | 0.51 | Const./37/Sanction/2021-22 18.11.2021 | 23.11.2021 | Yes | 15.12.2021 | 0 | 0.51
95 | 088-19 | Tiruchirappalli (P.) Zone | Tuticorin | Revalidation of A/a & E/s for the proposal of upgradation of Customs office buiding (Old Buildings-B Wing), Tuticorin for Rs.58,24,000/-reg. | R&M | 0.59 | .- | 0.09 | 42/2021-22 20.07.2021 | 29.07.2021 | No | NA | 0 | 0.09
96 | 301-19 | Tiruchirappalli (P.) Zone | Tuticorin | Revalidation of Providing barrier free access (Lift & toilet for disabled persons) to Customs office, Cuddalore-submission of estiamte of A/a & E/s. | R&M | 0.7 | .- | 0.07 | 125/2021-22 18.11.2021 | 29.11.2021 | No | NA | 0 | 0.07
97 | 090-19 | Vadodara CGST | CGST Vadodara-I | Revalidation of Repairs/Upgradaton of fesidential quarters and other works in the campus of CGST Bhawan at Nadiad under Vadodara-I (Gujarat)-reg. | R&M | 0.6 | .- | 0.44 | 43/2021-22 20.07.2021 | 29.07.2021 | Yes | 23.11.2021 | 0.16 | 0.28
98 | 003-18 | Visakhapatnam CGST | Tirupati | Construction of office building at Anantapur, Andhra Pradesh | Construction | 7.07 | 5.4 | 1.3 | Const./26/Sanction/2021-22 18.08.2021 | 25.08.2021 | Yes | Oct, 2021 | 1.3 | 0
99 | 247-16 | Visakhapatnam CGST | Tirupati | Construction of boundary wall alongwith leveling work & Borewell for office building and staff quarters for CGST Division and ranges at Kadapa | Construction | 0.64 | NA | 0.64 | Const./31/Sanction/2021-22 01.10.2021 | 07.10.2021 | Yes | 08.11.2021 | 0 | 0.64
100 | 284-21 | Visakhapatnam CGST | Tirupati | Construction of compound wall along with gat for GST office building and staff quarters at Tirupati Comm'te | Construction | 0.33 | NA | 0.33 | Const./33/Sanction/2021-22 13.10.2021 | 14.10.2021 | Yes | 08.11.2021 | 0 | 0.33
101 | 129-12 | Viskhapatnam CGST | Tirupati | Construction of 7 nos. Type-IV and Guest House for CGST Division, Kurnool (Tirupati Commissionerate), Andhra Pradesh | Construction | 3.96 | 3.02 | 0.25 | Const./23/Sanction/2021-22 06.08.2021 | 13.08.2021 | Yes | 08.09.2021 | 0.25 | 0