## Sheet1
Status of Vacant land
S.No | Zone/Directorate | Commissionerate | Reference letter dated from the concerned Comm'te | Details of land purchased |  |  | Purchase (Official/ resiential use) | Date of sanction order | Amount of penalty,if any paid | Reasons for Delay in construction | Likely date of commencement of construction
|  |  |  | Area (in sq. mtrs.) | Cost | Location & Address
1 | Ahmedabad C.Excise Zone | Ahmedabad-I | 24.10.13 | Nil
|  | Ahmedabad-II |  | Nil
|  | Ahmedabad-III |  | 5600 | 62,23,600/- | Mehsana Division, C.Excise, Ahmedabad-III Commissionerate, Ahmedabad Zone (R.S.No. 1660) | Office cum residential | ___ | _____ | _____ | The PE has been forwarded to the Ministry but the same has come back with some objections. Correspondences with CPWD in progress.
|  | Bhavnagar |  | 4046.86 | Free of cost, allotted by State Govt. | Revenue Survey No. 66, Mahuva Road, Opp. Pathikashram, Sawarkundla, Dist. Ameli | ___ | _____ | _____ | Since no offices at Sawarkundla, this office has proposed to DG (H&W), New Delhi for handing over the land to Dist. Collector of Amreli | ______
|  |  |  | 4877.4 | Rs. 167225/- | Survey No. 62, Fulsar Village, Dist. Bhavnagar | ___ | _____ | _____ | Land is in the name of Income tax Deptt. The land was taken for constructing res. qtrs.but as per CPWD, Bhavnagar Letter F. No. 23(28)/BN/CSD/2004/05/57 dated 19.05.2004, the above land is un-suitable for cosntruction of qtrs./offices. Hence, may be surrender to Income Tax | ___
|  |  |  | 7104.26 | Rs. 6.39 cr.(for 99 years lease with 1.5% of total purchase priceapyable as annual lease) | Plot No. 1685 Paiki, Nr.Sardarnagar Circle, Bhavnagar | ___ | _____ | _____ | Boundary wall has been constructed pliance for ofice bldg. has been prepard by CPWD, Mumbai work on PE under progress with CPWD gandhinagar. | ___
|  | Rajkot |  | Nil
|  | Ahmedabad (Service Tax) |  | Nil
2 | Bangalore C.Excise Zone | Bangalore-I, | 11.10.2013 | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
|  | Bangalore-II |  | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
|  | Bangalore-III |  | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
|  | Bangalore (Service Tax ) |  | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
3 | Bhopal C. Excise Zone | Bhopal | Not Received
|  | Indore | Not Received
|  | Raipur | Not Received
4 | Bhubaneswar C.,C.Ex & Service Tax Zone | Bhubaneswar-I | Not Received
|  | Bhubaneswar-II | Not Received
5 | Chandigarh C. Excise Zone | Chandigarh-I | 22.10.13 | 1257.67 | 1.94 cr. | Plot No. 1625-27, Sector-39B, Chandigarh | Residential use | 30.09.2008; Ministry's F.No 203/9/2007.Ad.VIII.EC | 0.48 | Non-accordance of approval for layout plan by U.T.'s Estate Office | Immediately after layout plan is approved by the U.T. Estate Office
|  |  | 22.10.13 | 1225.95 | 0.019 cr. | Sector-37-C,Chandigarh | Residential use | 28.03.1989;Ministry's F.No 203/25/1988/Ad. VIII(EC).07.04.2006 | Nil | Original purpose of construction Type-I houses became irrelevant by the date of posession. Request to change the use to construct a community hall not aceeded by U.T. | Only afterconstruction of community hall is allowed by the U.T. Eastate Office.
|  | Chandigarh-II | No Vacant Land
|  | Ludhiana | 22.10.13 | 24281.138 | 6.89 cr. | Guru Gobind Singh Avenue Jalandhar | Official cum Residential use | 01.01.2001 | Nil | Earlier there was proposal for construction of Office-cum-residential building for CEX Comm'te,Jalandhar. After re-structuring of Comm'te, CEX, Jalandhar was abolished and at present there is only C.Ex Division. It is yet undecided wether Office-cum-residential building for C.Ex. Division,Jalandhar or view of the forthcoming Cadre-Restructuring. | N.A.
|  | Amritsar | 22.10.13 | 2112.84 | 0.36 cr. | Ranjit Avenue Ajnala Road, Amritsar | Residential use | Ministry vide letter F.No. 916/03/03 dated 03.12.2012 Sanctioned an amount of Rs. 24,91,200/- for boundary wall. | Nil | Proposal under construction of residential quarter for Commissioner of Customs, Amritsar and Community Hall in the vacant land of 2112.84 Sq. Meters. | N.A.
|  | Jammu | 22.10.13 | 8034.56 | 0.32 cr. | Adjacent to SBI Colony,Rajinder Nagar, Phase-I,Ban Tatab, Jammu | Residential use | 23.01.1995 | Nil | Proposal for construction of residential colony was submitted to DGHRD, New Delhi for A/A & E/S of Rs. 29,19,12,300/-. Some shortcoming/deficiencies were noticed by the DGHRD for which a fresh proposal is required to be submitted and the same is under process and would be submitted very soon. | A fresh demand survey has been conducted and requirement sent to CPWD for seeking feasibility report which has not been received so far.
6 | Chennai C. Excise Zone | Chennai-I | Nil
Chennai-II
Chennai-III
Chennai-IV
|  | Pondicherry | 30.12.13 | 2021 | 2.64 cr. | WardNo. F,Block 7,Revenue VIII,Colas Nagar, Puducherry | Vacant Land | - | - | Under Litigation. The Hon'ble District Munsif court dismissed the suit for non-appearance of the party when the case came up for hearing. However,the party field pettition for restoration of the case for trail, which as learnt from the Addl. Central Govt. Standing counsel has been taken on file by the Hon. court for further proceeding. | -
|  |  |  | 430 |  | Ward No. F,Block 8, Revenue VIII,Colas Nagar, Puducherry |  | - | -
|  | Chennai (Service Tax) | Not given.
7 | Cochin C. Excise Zone | Calicut | Not Received
|  | Cochin C.Excise | Not Received
|  | Cochin Customs | Not Received
|  | Cochin Customs (Prev.) | Not Received
|  | Thiruvananthapuram | Not Received
8 | Coimbatore C. Excise Zone | Coimbatore | 17.10.2013 | Nil
|  | Madurai | 17.10.2013 | Nil
|  | Salem | 17.10.2013 | 4047 | Rs. 22,65,120/- | Block No. 39 & 42,T.S. No. 4/3A & 2/9, Calicut Main Road,Metturdam, SalemDist | Construction of Office cum residential accomodation for Mettur I & II Ranges | F.No. 203/16/97- Ad.VIII(EC) dated 15.06.1998 for purchase of land and F.No 202/7/2001-Ad. VIII(EC) dated 26.08.2002 towards A/A for construction. | Nil | In view of the fact that there is no cost saving in the construction of Office building with residential quarters at Mettur,the proposal has been withdrawn and intimated to DGHRD,New Delhi vide CCE,Salem letter C.No I/4/14/99Admn.PF.I dated 08.01.2010. | -
|  | Tirunelveli | 17.10.2013 | 12233 | Rs. 25,50,000/- | S.No.331/1 and 331/2, Catholic Centre, Thittankulam Village, Tutirorin Road, Kovilpatti | Office building/Residential use | 19.06.1997 | Nil | No approach road to the site. Hence, preliminary estimate (amount of Rs.25,86,400/-) for approach road to the site has been received from the CPWD,Madurai on 03.10.2009. Besides, all Associations have opposed the proposal for construction of staff quarters at Kovilpatti. The reasons stated by the association are that: 1. The proposed land is far away from Kovilpatti town. 2. The area is full of bushes thereby exposing the inhabitants to risk. 3. The place is not safe and secure. 4. There is no access to facilities regarding transport,education,shopping and recreation. 5. There is no access towards obtaining clean drinking water. Hence, the proposal to build quarters at the said land is being dropped fro the time being and the same had been communicated to this office vide CCE,Tiruneveli letter 12.09.2008. For approach Road,CCE,Tirunelveli made a reference to the Assistant Commissioner of CEx. Kovilpatti to pursue the local panchayat/Municipal authorities about the feasibility of laying approach road of 156 Mtrs from the main road to the proposed site for Kovilpatti division. It is ascertained from the local Panchayat and State High-way authorities; permission is required to be obtained from them in the prescribed format. Furthermore, CCE,Tirunelveli made a reference to the CPWD to get particulars mentioned in the formats as required by the local panchayat office. | -
|  | Trichy | 17.10.2013 | Nil
9 | Delhi C. Excise Zone | Delhi-I | 21.11.2013 | 17831.25 | 3.38 cr. | Plot No. IH-1.Sector-9, Dwarka,New delhi | Residential | - | DDA has demanded an interest of Rs. 77,57,191/- on the non payment of ground rent which has not been paid yet. | Administrative approval and Expenditure Sanction from DGHRD is pending. | Not Known
|  | Delhi-II | 21.11.2013 | 744 | 2.54 cr.(Purchased on prepetual lease basis) | Plot NO. 1,Retail Business Centre, Nangal Raya, Janakpuri, Delhi | Office Building | 04.02.2004 | Nil | Process of seeking necessary approval is under progress. | 2013-14
|  | Gurgaon (Delhi-III) | Not given.
|  | Faridabad (Delhi-IV) | 21.11.2013 | 14164.05 (But actual area found to be 16875.46) | 2.36 cr. | Sector-48,Faridabad | Residential | 28.06.1995 | Nil | HUDA has demanded as Addl. amount of Rs. 28551933/- towards increase area cost,extension fee and penality. Deptt.has protested the high before Estate ofifcer, HUDA | Not Known
|  | Panchkula | 21.11.2013 | 5743 | 3.39 cr. | Sector-25,Panchkula | Office Building | 17.11.2011 | 57,500/- | The proposal has been forwarded by Panchkula Commissionerate to DGHRD on 11.07.2013 for sanction of funds. | Not Known
|  | Rohtak | 21.11.2013 | 16923.8 | 4.93 cr. | Sector-3,HUDA Rohtak | Official-cum- Residential | 30.03.2009 | Nil | Process of seeking necessary approval is under progress. | Within 6 months from the date of admistrative approval from HRD.
|  | Delhi (Service Tax) | Not Given
10 | Hyderabad C. Excise Zone | Hyderabad-I | Not Received
|  | Hyderabad-II | Not Received
|  | Hyderabad-III | Not Received
|  | Hyderabad-IV | Not Received
11 | Jaipur Central Excise Zone | Jaipur-I | Nil
|  | Jaipur-II | 13.12.13 | 3952.13 | 76.54 Lacs+ 77.58 lacs lease rent = 154.12 Lacs | Block-H,Sector-14, Goverdhan Vilas Udaipur | Commissionerate Office at Udaipur | 18.04.2000 | Nil | Expenditure Estimates for construction amounting to Rs. 6,08,01,700/- was forwarded to Directorate of Housing and Welfare, New Delhi on 03.09.2007 for approval & sanction. The Housing of Welfare, New Delhi vide letteer dated 01.07.2008 requested for submitting the same which is still awaited. The Board vide letter No. A-11019/06/2008-AdIV dtd. 17.06.10 has decided to defer the shifting of the Commissionerate Hqrs. from JPR to UDR and decided to maintain status quo for the present. CPWD has been requested to submit the revised proposals/estimates as per the norms of GRIHA. | -
|  |  |  | 2884.64 | 0.2049 Crore | Plot No.429-439, Sector-5,Gandhi Nagar,Chittorgarh | Residential quarters at Chittorgarh | 12.06.2011 | Nil | The modified estimate for construction of 16 residential quarter for staff/ officers of Central Excise Division of Chittorgarh amounting to Rs. 3,51,67,000/- received from CPWD vide letter dtd. 25-10-12 and information received in prescribed format A on 17.12.12 has already been sent to DGHRD vide letter dated 01.03.2013. DGHRD vide their letter dated 18.02.2013 has made few quaries which are yet to be replied for want information from CPWD. | -
|  |  |  | 1858.06 | Rs. 16,66,665 | 11,Azad Nagar, Near Panna dhay Bhilwara | Division Office at Bhilwara | 13.12.2000 | Nil | Preliminary estimate amouting to Rs. 3,93,90,000/- for construction of office building was sent to DGHRD which are under process. The Drawing are to be got approved by the local authorities, amount of Rs. 171894/- for said approval has been got sanctioned. However, this amount has not been released by the CPWD for want of funds. As soon the said Drawings are got approved,point wise reply to the querries raised by the DGHRD shall be sent. | -
12 | Kolkata Central Excise Zone | Bolpur | Not given
Haldia
Kolkata-I
Kolkata-II
Kolkata-III
Kolkata-IV
Kolkata-V
Kolkata-VI
Kolkata-VII
Siliguri
Kolkata (Service Tax)
13 | Lucknow C.Excise Zone | Allahabad | Not given
Kanpur
Lucknow
14 | Meerut C.Excise Zone | Ghaziabad | Not given
|  | Meerut-I | 13.12.13 | Nil
|  | Meerut-II |  | Not given
|  | Noida | 23.12.13 | Nil
15 | Mumbai -I , C.Excise Zone | Mumbai-I | 24.10.2013 | 8085 | Rs. 5779 | Survey No. 246 (Pt). Kanjur Village,Bhandup ( E), Mumbai-400042 | Residential | 06.02.1993 | Nil | A proposal for construction of 90 nos. of Qtrs. Was forwarding to Commr. (H&W) in the year 1998. However, the same was not approved & in the year 2008 it was informed by Commr. (H&W) to review the proposal and submit a fresh proposal in view of the likely escalation of cost. Threafter, it was decieded to secure the plot first by constructing boundary wall to avoid down. The administrative approval for construction of boundary wall has been sanctioned by DGHRD recently in August 2013. | N.A
|  | Mumbai-V | Not Given
|  | Thane-I |  | 2503.14 | Rs. 76070 (Book value) | Chendani Bunder, Mithanagar Road, Thane ( E ) (Survey No. 37 & 38A) | Office Building | 23.10.2007(Transferred from Salt Deptt.) | 0 | Approval for construction of Office Building was granted by Under Secreatary to GOI vide letter F.No. 915/12/LAND/Thane-I/HW/07 dated 23.10.2007. Proposal for office building sent to CPWD and the same is pending. | N.A
|  |  |  | 5159.7 | Rs. 500 (Book value) | Chendani Bunder, Mithanagar Road, Thane(E) (Survey No. 214) | Comes under CRZ and therfore cannot be developed. Standing Cord. Committee has been requested for consolidation of the plots with the Salt Deptt. | Transferred from Salt Deptt. on 15.07.1989 & 30.01.1990 | 0 | Vacant | N.A
|  |  |  | 438.1 | Rs. 514(Book value) | Chendani Bunder, Mithanagar Road, Thane(E) (Survey No. 216) | do- |  | 0 | Vacant | N.A
|  |  |  | 1680 | Rs. 16,80,000 (Book value) | Chendani Bunder, Mithanagar Road, Thane(E) (Survey No. 2000) | do- |  | 0 | Vacant | N.A
|  | Thane-II |  | 4553 | Rs. 6,83,000 | Plot No. 94,MIDC, Boisar,Dist- Thane | Office Building | Nil | 1,21,88,400/- alongwith interest of Rs. 59,55,100/- (interest calculated upto 31.03.2013) Not paid | Administrative approval was granted by Ministry on 25.03.1995 and 24.05.1995. However, the CPWD vide their letter dated 09.08.2012 has informed presently no found is available with them for this work. | N.A
|  |  |  | 2278 | Rs. 2,27,800 | Plot No. RB-12,MIDC, Boisar,Dist- Thane | Res. Quarters | Nil | Penalty not worrked out by MIDC,since Deptt. has not requested for extension with MIDC. | The plots purchased for residential quarters for officers and staff of Central excise Deptt. The preliminary estimates for construction of bulding were received from CPWD in the year 1998 for Rs. 5.51 corores. Due to less response from the staff, the proposal was scrapped by the Ministry on 08.03.2006. Again the possibility of utilisation of these two plots for residential quarters were placed on 25.03.2013 with DGHRD,New Delhi. | N.A
|  |  |  | 5500 | Rs. 5,50,000 | Plot No. 35/11 to 35/15,MIDC, Boisar,Dist- Thane | Res. Quarters | Nil |  |  | N.A
Mumbai (Service Tax-I)
Mumbai (Service Tax-II)
16 | Mumbai-II , C.Ex Zone | Belapur | 09.10.13 | Nil
|  | Mumbai-II | 09.10.13 | Nil
|  | Mumbai-III | 09.10.13 | 8214 | 0.00260 crores | Survey no. 389,Mithagar Road, CTS 1069,Mulund (East), Mumbai | Office/residential building | 09.10.84 | Nil | Central Excise Department purchased land in the year 1985 from the Salt department. Land admeasuring 8214 sq m was handed over to C.Excise on 27.03.1998 and the samw was entered in the records of City Survey dept on 05.10.2001. However, Govt of Mahrashtra issued Gazette notification no. TPB-4932/6096/4D-11(RDP) dated 15.04.1993 and subsequently issued corrigendum no. 4932/6039/UD-11(RDP) dated 24.12.1995 notifying that a piece of land measuring 3300 sqm. is reserved for purpose for playground as per master plan of MCGB. Correspondences are being made for denotifying. Efforts are being made to demarcate the plot after survey so that boundary wall could be constructed for stopping the encroachment. A/a & e/s for an amount of Rs. 81,06,468/- has been made vide letter dt. 16.08.12.
|  | Raigad | 09.10.13 | 20000 (leased property) | 2.20 cr | Plot No. 16,Sector-7, Kharghar, Navi Mumbai-Near Kharghar(Harbour) Rly,Station | Residential | 06.01.1992 | Nil | CIDCO did not issue non-encumbrance Certificate but has faised demand of Rs. 5.71 cr. Towards Additional Lease premium, service charge etc., the sanction of which is givenby Ministry and duly revalidated for 2013-14. However, the disbursement of payment of the same is yet to be received from CPWD. Payment will be made to CIDCO as and when received.
17 | Mysor C.Ex. Zone | Mysore | 11.10.2013 | 0.08 acres | Free of Cost | Survey No. 87/19 of Karavale Badaga Village of Madikeri | Official | 04.06.2013 | N.A. | Recently alloted | Not yet fixed
|  | Mangalore |  | 190971.16 | Acquired before Independence & cost is not reflected in the Asset Register 2013 | Survey No. 70A & 71A of Cambuli Village of Castle Rock, Uttara Kannada Dist | Official | Acquired before Independence | Nil | Proposed for setting up of Sniffer Dog Squad | Final proposal is yet to be received
|  | Mangalore |  | 486 (not 480 as shown in Asset Register 2013) |  | Survey No. 55-60, Udupi Town(*) | Official & Residential | Acquired before Independence | Nil | The preliminary estimate has already been forwarded for Administrative approval | Shortly
|  | Belgaum |  | 10253 | 11.47 | Survey No. 8,Ward No. 5,Nalla Cheruvu, Bellary | Official & Residential | 04.07.1997 | Nil | The site was alloted by Govt of Karnataka during 1997 for construction of office building & residential quarters and a compound wall was constructed. Proposals are sent to DGHRD since 2004 for approval and a revised proposal was submitted on 24.05.13. It was learnt that the Deputy Commissioner, Bellary Dist vide order dt 28.04.12 has cancelled the allotment quoting that the dept is having own land/building and the said site has not been utilisedwhich is not factually correct and without giving any information to the dept. The jurisdictional AC,Bellary Divn is directed to request DC,Bellary Dist for estoration of allotment for construction of office & residential quarters. No penalty has been imposed by the State Govt. | N.A
|  | Belgaum |  | 5351 | 9.4 | Plot No. 309, Naubad,Bidar | Official & Residential | 11.07.2002 | Nil | The deficiencies pointed out by DGHRD for the prposal sent on 11.02.13 has been communicated to CPWD,Mysore & JAC Gulbarga for doing the needful. | N.A
|  | Belgaum |  | 4000 | Free of Cost | Unit No. 1,Sector-50 of BTDA,Bagalkot | Official & Residential | 26.03.2003 | Nil | A proposal has been submitted to DGHRD on 31.05.13 seeking A/A & E/S. Permission has to be obtained from local municipal authorities and as soon as permission is received, reply will be submitted to DGHRD. | N.A
18 | Nagpur C.Ex. Zone | Aurangabad | 17.12.2013 | 5292.37 | 32.18 Lakhs | Survey No.51 Village Vasarni,CIDCO, New Delhi | Office building and Residential quarters of Assistant Commissioner,Nanded | 19.07.2000 | Rs. 51,48,418/- as penalty/Additional lease premium. | Proposal for Administrative approval and expenditure sanction has benn submitted to DGHRD | 36 months from receipt of approval/sanction of Board,communicated by DGHRD.
|  | Aurangabad |  | 2310.84 | 28.78 Lakhs | Survey No.105, Chandani Chouk, Near Church, Ahmednagar | Office building of Assistant Commissioner,Ahmednagar | 20.05.2010 | Not yet | CPWD is yet to submit complete proposal. | -
|  | Nagpur | Nil
|  | Nashik | Nil
19 | Pune C.Ex. Zone | Goa Customs | Nil
|  | Kolhapur | Nil
|  | Pune-I | Nil
Pune-II
|  | Pune Customs | 28.10.2013 | 300 |  | Jaigad. Old Jetty, S.No. 5-0,Mandavi,Jaigad | Opened land | NA | NA | NA | NA
|  |  |  | 300 |  | Jaigad. S.No-5-B,Pathwadi,Jaigad | Opened land | NA | NA | NA | NA
|  |  |  | 1000 |  | Jaigad.S.No.13-A,Pathwadi, Jaigad | Opened land | NA | NA | NA | NA
|  |  |  | 660 |  | Jaigad. S.No-42,Near Port office, Jaigad | Opened land | NA | NA | NA | NA
|  |  |  | 2400 |  | Jaigad. S.No. 95-1,Inside fort,Jaijad | Opened land | NA | NA | NA | NA
|  |  |  | 1470 |  | Ratnagiri, S.No. 483A,Near Sea Shore, Bunder Rd.,Ratnagiri | Opened land | NA | NA | NA | NA
|  |  |  | 180 |  | Ratnagiri, S.No. 498,Near Sea Shore, Bunder Rd.,Ratnagiri | Opened land | NA | NA | NA | NA
|  |  |  | 400 |  | Jaki Mirya. Jetty open land,S.No.63,Jaki Mirya, Ratnagiri | Opened land | NA | NA | NA | NA
|  |  |  | 2200 |  | Jaki Mirya. Open Land,S.No.68,Jaki Mirya, Ratnagiri | Opened land | NA | NA | NA | NA
|  |  |  | 847 |  | Sakhartar. Open Land S.No.55,Sakhartar | Opened land | NA | NA | NA | NA
|  |  |  | 1500 |  | Purnagad.S.No 34,Mouje, Ghera,Near lagoon shore | Opened land | NA | NA | NA | NA
|  |  |  | 200 |  | Ambolgad. S.No.38-90,Gaondar,Ambolgad | Opened land | NA | NA | NA | NA
|  |  |  | 630 |  | Shivare Khurd.S.No 79-1,Near Sogam wadi, Shivre Kurd,R'giri | Opened land | NA | NA | NA | NA
|  |  |  | 150 |  | Jaitapur.S.No.31,Opp S.G. Office,Jaitapur | Opened land | NA | NA | NA | NA
|  |  |  | 50 |  | Jaitapur.S.No.32,S.G. Office, Udalwadi, Jaitapur | Opened land | NA | NA | NA | NA
|  |  |  | 1240 |  | Jaitapur. S.No.2,Anantwadi, Jaitapur | Opened land | NA | NA | NA | NA
|  |  |  | 480 |  | Devgad.S.No 16A-13,Near Light House, Inside Fort Devgad. | Opened land | NA | NA | NA | NA
|  |  |  | 100 |  | Devgad.S.No 18-A-5,Near Light House, Inside Fort Devgad. | Opened land | NA | NA | NA | NA
|  |  |  | 780 |  | Gagan Bewada,S.No. 293,Lila Shankar Park, Gaganbawada | Opened land | NA | NA | NA | NA
|  |  |  | 80 |  | Malwan,S.No 37,Near to Jetty,Sarjekot | Opened land | NA | NA | NA | NA
|  |  |  | 7100 |  | Malwan,S.No 28,Sarjekot | Opened land | NA | NA | NA | NA
|  |  |  | 100 |  | Sawantwadi.S.No.51A-26,Bagbagiti,Satarda, Sawantwadi | Opened land | NA | NA | NA | NA
|  |  |  | 12 |  | Vengurla.S.No.45,Near Kinara Hotel, Near Port, Vengurla | Opened land | NA | NA | NA | NA
|  |  |  | 680 |  | Vengurla.S.No.55,Shiramwadi, Vengurla | Opened land | NA | NA | NA | NA
|  |  |  | 1775 |  | Vengurla.S.No.600,Mandavi,Vengurla | Opened land | NA | NA | NA | NA
|  |  |  | 200 |  | Redi.S.No.1-2B,Khalchi Ker,Near Shiroda, Redi. | Opened land | NA | NA | NA | NA
|  |  |  | 760 |  | Redi.S.No. 33B Tak,Arawali,Shiroda | Opened land | NA | NA | NA | NA
|  |  |  | 700 |  | Redi.S.No.3-2,Behind Mauli Mandir, Nagolewadi,Redi | Opened land | NA | NA | NA | NA
20 | Ranchi C.Ex. Zone | Jamshedpur | 02.01.2014 | Nil
|  | Patna |  | 1457 | Rs. 4500 | Sighara under Mauzzafarpur Div. | Vacant Land | N.A.D.O.A 15.11.1965 | No | These lands were acquired when tobacco was unedr C. Ex. Control. Now, these are un-utilized because they are located far from Div. & range office.
|  |  |  | 1255 | Rs. 1084 | Rajapakar under Muzzafarpur Div. | Vacant Land | N.A.D.O.A 06.01.1954 | No
|  |  |  | 1781 | Rs. 2666 | Patepur under Muzzafarpur Div. | Vacant Land | N.A.D.O.A 12.02.1964 | No
|  |  |  | 44.53 | Rs. 0.82 cr. | Dholi under Muzzafarpur Div. | Vacant Land | N.A.D.O.A 27.12.1965 | No
|  |  |  | 1264 | Rs. 3480 | Baghra under Laheriasaraia Div. | Vacant Land | 30.07.1954 | No
|  |  |  | 22428 | Rs. 55,000 | New Sipai Tola, Purnia under Bhagalpur Div. | Vacant Land | 12.04.1965 | No | Res. Flats also constructed within the campus on 1012 sqm. of land.
|  | Ranchi | Nil
21 | Shillong C.Ex. Zone | Dibrugarh | 09.01.2014 | Not given
|  | Guwahati |  | Not given
|  | Shillong |  | Nil
|  | Shillong Customs (Prev.) |  | Not given
22 | Vadodara C.Ex. Zone | Daman | 08.01.2014 | 3686 | 10689400 | R.S. No. 193, Kachigam Road, Vapi | Official and Residential | NA | NA | NA | NA
|  | Surat-I | Nil
|  | Surat-II | Nil
|  | Vadodara-I | Not given
|  | Vadodara-II | Not given
|  | Vapi | Nil
23 | Visakhapatnam C.Ex. Zone | Guntur | Nil
|  | Visakhapatnam-I | 05.12.2013 | 1500 | 0.01 Cr. | Plot No. 79,Survey No. 79 (Part)Pedamadaka Village,Nehru Marg, Steel Plant, Vizag | Official use | Preliminary estimates received from CPWD and sanction order being obtained. | No penalty paid | No delay | -
|  | Visakhapatnam-II | Nil
|  | Tirupati |  | 5556.9 | 1 Crore | Sy No.: 990/3A & 1991 Sangamesh Nagar,Old Town, Anantapur | Anantpur Divisional Officer and Staff Resiential Quarters | Rs. 7,43,12,000/- was sanctioned vide Lr. F.No. 916/55/Const/ Anantp3.ur/HW/2006,Dt. 06.03.2012. | Nil | Designs were finalised in consultation with CPWD. The CPWD official has informed that the estimation proposal in respect of staff quarters have been finalised and tenders have been called for and in respect of office building the same may be finalised shortly. | Less than a year
|  |  |  | 607.3 | 0.054 Cr. | Sy No.:584/3 & 583/2,B Camp,Kallur Village, Kurnool | Staff Quarter | Awaiting Administrative and finacial sanction for the construction of staff quarters. | Nil | The DGHRD has raised certain clarification and asked for received estimates from CPWD and the same are awaiting and as requested by DGHRD a revised proposal will be sent for the construction of staff quarters. | More than a year.
|  | Visakhapatnam Customs |  | 1090.21 | Nil (Land acquired on exchange of old Custom House to VPT) | Saligrampuram,Behind Port Stadium, Visakhapatnam | Residential | Administrative approval for exchange of Old Custom House land with VPT land was granted vide F.No. 915/14/land/VPT/HRD-ID/09 dated 18.11.2010. | Does not arise | Registration of subject plot is being pursued with VPT | Will commence after registration
24 | Ahmedabad Customs Zone | Ahmedabad | Nil
Customs (Prev.) Jamnagar
|  | Headquarter, Customs (Preventive), Jamnagar | 05.12.2013 | 10250 | 8.8 Cr. | Rajkot-Jamnagar Highway, Jamnagar | Office cum Residential | 23.06.2011 | - | - | Received A/A/ and E/S for construction of boundary wall; CPWD will start the work in near future;Preparation work of plan/maps for construction of oofice building/quarters is under progress with CPWD authority.
|  | Dwarka |  | 4047 | 0.11 Cr. | Dwarka-Jamnagar Highway, Nr. Shishu Vihar | Office cum Residential | 09.05.2008 | - | The construction work of boundary wall has been completed by CPWD. However,the land is under litigation. The case is pending before SD,Khambhaliya. | -
|  | SG-Jafrabad |  | 4047 | 0.01 Cr. | New Jetty, Jafrabad | Office cum Residential | 09.05.1991 | - | - | The Superintending Engineer,CPWD,Gandhinagar has submitted the final PE during the month of Feb-2013;proposal for Administrative Apprpval and Expenditure sanction for construction of office building cum residential quarter to Ministry through Chief Commissioner Office Ahmedabad is in progress.
|  | CH-Okha |  | 3108 | 0.03 Cr. | Opp. Old GEB Station,TR Colony,Okha | Office cum Residential | 21.05.1996 | - | - | The work has been completed and is being used. Though we have started using the constructed premises,correspondence with respect to Building Usage Permission is going on with the Okha Nagarpalika.
|  | SG-Dwarka |  | 684.92 | 0.11 Cr. | Survey No. 3935,Opp. Gayatri Temple,Dwarka | - | Possession was taken by the Deptt. from erstwhile Baroda State | - | At present the office is working in port cabin situated in this land. | -
|  | Rupen(Dwarka) |  | 140.12 | 0.02 Cr. | Survey No. 17, Old Customs House,Rupen (Dwarka) | - | Possession was taken by the Deptt. from erstwhile Baroda State | - | At present the office is working in port cabin situated in this land. | -
|  | CD-Porbandar |  | 3 Acres (12140.569 Sq. Mtrs.) | 0.0085 Cr. | Customs Division Office,Opp. Civil Air Port,B/h N.K. Mehta Hospital Porbandar | Office | 1987 | - | - | Construction work has been carried out and completed in 1991.
|  | CH-Veraval |  | 1000 | 0.04 Cr. | Plot No.176,Survey No. 1537,Veraval | Office/Residential | 25.11.2010 | - | - | Construction work has been completed on 27.07.2013,Building Utility Certificate for use of building from local authority is awaited.
|  | Shore Guard-DIU |  | 978 | Without cost alloted by Admn. of Daman vide letter No. 4B-20/172-168-B dated 07.05.1968 | Plot No.PTS-61/24,at DIU Administration,DIU | Office | Before 1961 | No | N/A as the department acquired ready built premises for office use from the beginning | The ownership of the propoerty lies with the Diu Administration Department;it was given purely for running the office only;no rent is being charged;only requirement is to fulfill the responsibility of maintenance and required alterations of the property for which Ministry has sanctioned Rs. 40,64,742/- on 26.04.2011 for repairing. The matter is under correspondance with the CPWD. Repairing work of godown has been finished.
|  | CH-Ghogha |  | 1858.04 | 0.0015 Cr. | Port Jetty,Ghogha | Office | 13.04.1964 | No | - | Letters dated 03.03.2011 and 27.02.2012 has been issued to the executive engineer,CPWD,Rajkopt for dismantling and reconstruction of office but no action has been taken yet
|  | Kandla |  | 1500 | 45000 Cr. | Bhachau Survey No. | Office as well as Residential Quarters | F.No.203/31/93-D-VIII (EC)Dated 22.11.94 | - | Proposal for construction of office cum residential quarters has already been sent vide this office letter F.No I/4-5/88/L&B-Pt.II Dated 09.11.2012 to CPWD.
|  |  |  | 500 | 10000 Cr. | Nr. Leuva Patel Hospital Mundra | Office | F.No.203/09/88-AD-VIII(EC)Dated 25.03.88 | - | Proposal for construction of office cum residential quarters has already been sent vide this office letter F.No I/4-1/2002-03/Admn-Pt.II Dated 08.02.2013 to CPWD.
|  |  |  | 8100 | 8910000 Cr. | - | Residential Quarters | F.No.203/09/2000 -AD-VIII(EC) Dated 27.04.01 | - | do-
|  |  |  | 2000 | 1200000 Cr. | - | Office as well as Residential Quarters | F.No.201/06/96-D-VIII (EC)Dated 8.7.97 | - | Proposal for construction of office cum residential quarters has already been sent vide this office letter F.No. I/4-11/88/Admn.Pt.II | Pending with CPWD
25 | Bangalore Customs Zone | Bangalore |  | Not given
Mangalore
26 | Chennai Customs Zone | Chennai (Airport & Air Cargo) | 11.10.2013 | Nil
Chennai (Port-Import)
Chennai (Port-Export)
27 | Customs (Prev.) Chennai Zone | Tiruchirapally |  | 950 | Present market value Rs. 60/- per sq. ft. total cost worked out to Rs. 6,13,320/- and guideline value for entire survey is Rs. 200/- per sq. ft. | Survey No. 77, Alaganavayal of Kattumavadi Salt Dept. Avudaiyar koil taluk, Pudukottai Dist. | Ofice cum residential | 22.02.1990 | Nil | Land is not in Dept. name in State Revenue records, action being taken for obtaining Patta in Dept. name | ___
|  |  |  | 155 | Present market value Rs. 10/- per sq. ft. total cost worked out to Rs. 1,66,84/-obtained free of cost from Natham Poromboke of State Govt. | Survey No. 235/228, Ammapattnam Avudaiyar koil taluk, Pudukottai Dist. | Office | 1997 | Nil | The land is available from 10 mtr.from sea. As per costal regulation act no const. can take place within 500 mtr. from sea. | ____
|  |  |  | 2347 | 57,994/- | Ranghanathpuram, Semangalam (Rev. village) Vanur Taluk, Villupuram Dis. | Frontior land | ____ | ____ | _____ | ___
|  |  |  | 17442 | 26,16,300/- | 12,RS. No. 166,167/2,168/2,168/4 & 174/2, Madalapet, (Reddichavadi Cuddalore Dist.) | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 49088 | 1,32,29,216/- | 36,RS. No. 1779,1781,1782/1B,1782/2B,1784/1,1784/2B,1785/1B,1785/2,1787,1789,1791,1794,1795,1796,1798,1861,1862,1863,1864 & 1869 Manjakuppam Village, Cudalore Dist. | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 1578 | 39,05,550/- | 35,RS. No.33/1,34/1,34/4,34/16,42/1,87/3,88/5,89/7,89/13,91/3,92/1,93/1,101/1 & 101/9 Gundupalavadi, Cuddalore Dist. | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 11534 | 1,24,56,720/- | 31,RS. No. 63/19,63/22 & 63/24 Periakanganam Kuppam, Cuddalore Dist. | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 78671 | 48,59,507/- | Rs. No. 12,18,19,20,24,25,64,66,67,68,72,73,89 & 90 pagandi Village, Panruti Taluk, Cuddalore Dist. | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 25495 | 22,04,507/- | Rs. No. 2,6,8,10,12,43,2,3 & 4 Vanbakkam, panruti Taluk, Cuddalore | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 27680 | 23,93,765/- | Rs. No. 2,5,7,4,5 & 14 Muligrampet, Panruti Taluk Dist. | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 26102 | 19,34,041/- | 24, RS. No. 227,229,230,231,232,233,234 & 235 Mela Alaginanthan, Cuddalore Dist. | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 33710 | 20,82,266/- | 25, Rs. No. 107,112,114,117,118,128,131,132,148,150,152 & 154 Vellapackam, Cuddalore Dist. | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 16268 | 20,09,911/- | Rs. No. 12,14,15 & 16 Maruthadu, Cuddalore Dist. | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 8701 | 93,97,080/- | 28,RS. NO. 5,6 & 7 Veli Semmandal, Cuddalore Dist. | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 7042 | 1,13,22,830/- | 29 Rs. No. 1967,1987,1990,1991,1992,1993 & 1994 Vilvarayanathan, Cuddalore Dist. | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 9753 | 12,04,983/- | 30, Rs. No. 1865/2,1865/1A2A,1870,1871,1873,1874,1875,1876,1877,1878,1965 & 1966 Uthiramanickam, Cuddalore Dist. | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 67501 | 1,00,07,698/- | Rs. No. 9,10,16,17,20,29,30,32,34,38,39,48,51,55,57,58 & 60 Nathapattu, Cuddalore Dist. | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 40752 | 50,34,909/- | Rs. No. 5,8,9,10,11,1/1, 1/3,1/2,2/1,2689 & 12, Thirukandeswarani, Panruti Taluk, Cuddalore Dist. | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 3035 | 16,38,900/- | Ts No. 635/2A, 635/2B &635/3, Thirumullaivasal Village, Sirkali Taluk, Negapattinam Dist. | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 4694 | 1,76,83,750/- | Beach Road, portonova, Chidambaram Taluk | Frontior land | ____ | ____ | ____ | ____
|  |  |  | 10117 | 13,06,77,600/- | No. 60, Mohan Singh, Street, Cuddalore OT, Cuddalore Dist. | Frontior land | ____ | ____ | ____ | ____
|  | Customs Division-Nagapattinam |  | 201 | Not known (ascertained from the sub-rgister, Muthupet that it is Govt. Land and so value was given in the guidelines, but as village highest market value is Rs. 2265/- per sq. mtrs. As it is worked out to Rs. 4,55,265/- | RS. No. 428-B, 13, Thuraikkadu Village at Muthupet, Thiruthuraipoondi Taluk | Prior to Independence | ____ | ____ | ____ | Encroached by one Smt. Segu Ammal w/o Baba Mohideen Muthupet. The eviction proecedings pending in High Court Chennai. The earlier order are in favour of Dept.
|  |  |  | 932 | Not known (ascertained from the sub-rgister, Adhirampattinam that it is Govt. Land and so value was given in the guidelines, but as village highest market value is Rs. 754/- per sq. mtrs. As it is worked out to Rs.7,02,728/- | RS. No. 81/1 of 149 Eripurakkarai Village at Adhirampattinam, Pattukottai Taluk | _____ | 1963 | ____ | _____ | As of now, no field formation is functioning in Eripurakkarai or Adhiramapattinam
|  | Customs Division-Ramnad |  | 848 | State Porambokku land (i.e. free of cost book value 0.35 crores) | Survey No. 610/2 (old no. 762/2) Kanjirankudi Group, Keelakarai) | Office | ____ | _____ | The Sr. Architect, CPWD, Chennai requested to send plan for approval of const. of office bldg. | _____
|  | Customs Division-Tuticorin |  | 1719.9 | 12.98 lakhs | Survey No. 805/4, Beach Road, Keyalpattinam, Thiruchendur Taluk, Tuticorin Dist. | office | No reference is available, since the land is purchased before Independence | ____ | Requested Sr. Architect, Chennai for Preliminary Drawings | After getting Preliminary Drawings, it will refer to Board for approval for const.
|  |  |  | 2155.028 | Rs. 13.31 lakhs | Survey No. F37,F38 & F39 Colachel, Kanyakumari Dist. | ____ | No reference is available, since the land is purchased before Independence | _____ | ______ | After getting Preliminary Drawings, it will refer to Board for approval for const.
28 | Customs Delhi Zone | Delhi (Air Cargo-Import & Gen.) | 23.09.2013 | Nil
Delhi (Air Cargo-Export)
Delhi (ICD etc.)
29 | Delhi (Prev.) Zone | Amritsar | Not given
|  | Delhi (Prev.) | Nil
|  | Jaipur (Jodhpur) | 21.01.13 | 2000 | 0.14 Cr. | Customs Range, Udaipur | Official use | - | Nil | As per letter C.No. I-04 (15) Admn/Customs/1993/1588 dated 18.02.2010 of the Commissioner Customs, Jaipur process for construction of office building for Customs Range Udaipur has not been initiated because the Range office is working from Central Excise building and staff strength has also been reduced.
|  |  |  | 2149.565 | 0.05 Cr. | Cutoms Range, Nachna | Official use | - | Nil | Construction has not been initiated because after restructuring of the Customs Ranges, the work related with the Range office, Nachna has been ordered to be looked after by the Superintendent Customs Range, Pokran as per order C.No. I(15)1/Admn/Cus/2000/4326-4343 dated 16.06.2006.
|  |  |  | 392 | 0.12 Cr. | Customs Range, Anoopgarh | Official use | - | Nil | As per letter C.No. I-04(4) Admn/Customs/92/5992 dated 15.06.2010 of the Commissioner Customs, Jaipur process for construction of office building for Customs Range Anoopgarh has not been initiated because the staff strength has been reduced.
30 | Kolkata Customs Zone | Kolkata (Port) | Not given
Kolkata (Airport & Admn.)
Kolkata (Prev.)
31 | Mumbai -I Customs Zone | Mumbai (Mulund CFS & Gen) | 21.10.2013 | 54 acres i.e. 221219.16 sq. mtrs | No cost Land was transferred by the CPWD on 21.10.2003 | Custom Enclave Plot (Suleman shah Plot) Survey No. 146,Saltpan Road, wadala,Mumbai | office,Godown,residential quarter,sports complex and small primary school. | Nil | Nil | A/a & e/s of Rs. 10.49 crores of comprehensive consultancy services and enabling works towards construction of phasse-I i.e. office complex and godown has been accorded by the Ministry's letter F.No. 916/11/Const./HW/2005 Pt.II dated 9th July,2013.
|  |  |  | 9590.4 | Land stands in the name of collector of Cus. As per land revenue records book value of the land is Rs. 67.92 cr. As on 31.12.2010 as per ready recknoer but it is indicative only. | CTS No. 377, Survey No. 137 (pt.) at jaihind Nagar/Jawhar Nagar, Khar €, Mumbai |  | Nil | Nil | Property is under complete encroachment by slum dwellers. | Action under public premises (Eviction of un-authorized occupants). Act, 1971 is being intitiated. This ofice has requested DGHRD vide letter dated 11.06.2013 forof Estate officers.
|  |  |  | 3796.02 | Land stands in the name of collector of Cus. Since 1940 As per land revenue records book value of the land is Rs. 8.54 cr. As on 31.12.2010 as per ready recknoer but it is indicative only. | Cadasrtal Survey No. 1393, Mahim Port, Mahim (W), Mumbai |  | Nil | Nil | Property is under complete encroachment by slum dwellers. | Openion of Law Ministry with suggestive course of action communicated to DGHRD vide letter dt. 15.07.2013.
|  | Mumbai (Import) | Not given
Mumbai (Export)
32 | Mumbai-II , Customs Zone | Nhava Sheva (Import) | Not given
Nhava Sheva (Export)
33 | Mumbai-III, Customs Zone | Mumbai (Prev.) | 14.11.2013 | Nil
Mumbai Airport
Mumbai Aircargo (Import)
Mumbai Aircargo (Export)
34 | Patna Zone | Lucknow (Prev.) | Nil
|  | Patna (Prev.) | 30.12.2013 | 1671 | 0.96 cr. | Right side of LCS, Jogbani at PO, Jogbani, Dist. Araria | Propose examination yrd. | 25.07.2008 | Nil | Under Construction | __
|  |  |  | 11088.13 | This land was handed over by Indian Embassy, Birganj, Nepal in 2013. Proposal of const. of res. bldg. and allied infra. has been sent to CPWD Authority.
35 | Large Tax Payer Tax Unit (LTUs) | Bangalore |  | Not given
|  | Chennai | Nil
36 | DG of Systm & Data Management, Chanakya Puri, New Delhi |  | 11.10.2013 | Nil
37 | DG of Inspection, Cus. & C. Ex., Drum Shape Building, I.P. Estate, New Delhi |  | 04.10.2013 | Nil
38 | Directorate of Data Management, Cus. & C. Ex., G.K.-II, New Delhi |  | 27.09.2013 | Nil
39 | NACEN Faridabad |  | 06.01.2014 | Nil
40 | DG, Vigilance |  | 21.11.2013 | Nil
41 | Directorate of Legal Affairs |  | 29.11.2013 | Nil
42 | Directorate of General of Valuation |  | 13.12.2013 | Nil
43 | Directorate of General of S.Tax, Mumbai |  | 02.12.2013 | Nil